## Project Planner
[5 empty] | Period Highlight: | 30 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (1 units per week)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Handling class imbalance by GAN based Data Augmentation in Medical Images | 1 | 30 | 1 | 30 | 100%
Research Interest submision | 1 | 3 | 1 | 3 | 100%
Topic Submission | 4 | 4 | 4 | 2 | 100%
Exploring and finding the GAP in research area | 4 | 4 | 4 | 2 | 100%
Research proposal preparation | 9 | 6 | 9 | 6 | 100%
Literature reivew | 8 | 6 | 8 | 6 | 100%
Mid thesis preparation | 14 | 8 | 15 | 7 | 100%
Continue research review and research | 14 | 8 | 14 | 8 | 100%
Development environment setup | 15 | 1 | 15 | 1 | 100%
Dataset understanding and visualizatin | 16 | 1 | 16 | 1 | 100%
Understanding different GANs in detail | 17 | 3 | 17 | 4 | 100%
Preparing interim report | 19 | 3 | 20 | 2 | 100%
Final thesis preparation | 22 | 9 | 22 | 9 | 100%
Developing and Evaluating GANs And AE | 22 | 3 | 22 | 4 | 100%
Experimenting with GANs | 22 | 1 | 22 | 1 | 100%
Experimenting with AE | 23 | 1 | 23 | 1 | 100%
Experimenting with Integrated system of GAN and AE | 24 | 1 | 24 | 2 | 100%
Developing and Evaluating Classification Models | 25 | 2 | 26 | 1 | 100%
End to End development | 27 | 1 | 27 | 1 | 100%
Understanding output and deriving conclusion | 28 | 1 | 28 | 2 | 100%
Preparing final thesis report | 22 | 7 | 22 | 8 | 100%
Final thesis submission and video presentation | 29 | 2 | 29 | 2 | 100%